## Slide 1
Requirement Engineering
Lecture 11: Requirements Management
Prof. Dr. Benjamin Leiding
M.Sc. Anant Sujatanagarjuna
M.Sc. Chintan Patel

## Slide 2
General Requirements Engineering Process
Overview

## Slide 3
Lecture 11: Requirements Management
Content
Manage Requirements
Change Management

## Slide 4
Manage Requirements

## Slide 5
Manage Requirements
Motivation – Why do you need to manage requirements?
Number/scope of requirements and further information
Expected product lifetime
Rate of changes to requirements and related docs
Number of stakeholders
Availability of stakeholders
Heterogenous nature of stakeholder opinons
Future reusability
Number of expected releases
Etc.

## Slide 6
Manage Requirements
Motivation – What exactly needs to be managed?
Requirements
Epics
Definitions
Goals
Test Case
Assumptions
Use Case
User Story
Change Request
Issues
Architecture Description

## Slide 7
Manage Requirements
Definition – Management in Requirements Engineering
“The process of managing existing requirements and requirements related work products, including the storing, changing and tracing of requirements (traceability).”
Martin Glinz (2020) – A Glossary of Requirements Engineering Terminology (Standard Glossary for the Certified Professional for Requirements Engineering (CPRE) Studies and Exam)

## Slide 8
Manage Requirements
Information model - Simple
Based on Chris Rupp et al. (2021) – Requirements Engineering und Management – Das Handbuch für Anforderungen in jeder Situation (7th Edition)

## Slide 9
Manage Requirements
Information model – More complex
Based on Chris Rupp et al. (2021) – Requirements Engineering und Management – Das Handbuch für Anforderungen in jeder Situation (7th Edition)

## Slide 10
Manage Requirements
Standardized structures and templates
Volere
V-Modell XT
IEEE 29148-2018
Etc.
1. https://www.volere.org/
2. Der Beauftragte der Bundesregierung für Informationstechnik. V-Modell XT (o.J.), URL: https://cio.bund.de/Web/DE/Architekturen-und-Standards/V-Modell-XT/vmodell_xt_node.html
3. https://standards.ieee.org/ieee/29148/6937/

## Slide 11
Change Management

## Slide 12
Change Management
Overview
Various reasons for changes
  Errors or incomplete requirements
  Evolution of context
Changes are not a bad thing
  Stakeholders may gain new knowledge at later project stages
  Proofs interest/involvement of the stakeholders
Frequent changes are problematic
  Makes development in agreement with all stakeholders very challenging and time-consuming
  Indicator for bad process quality

## Slide 13
Change Management
Overview
Necessary to properly structure and process change requests for requirements
Structured process → Justifiable decisions if and how requests are approved
Changes may refer to:
  Individual requirements, e.g., change/addition/removal of a feature
  The requirements document itself, e.g., updating terminology

## Slide 14
Change Management
Change Control Board
Change control board as entity responsible for change requests
  Evaluation
  Decision making
May delegate tasks to another party
  For example, drafting of actual changes to the requirements
Decisions have to be negotiated and agreed upon
  Contractor
  All involved stakeholders

## Slide 15
Change Management
Change Control Board – Tasks
Change effort estimation
  Could be performed by third party
Evaluate change requests
  For example, effort/benefit ratio
Define requirements change and/or new requirements
  Based on the changed request
  Changes should be kept to a minimum
Decide about acceptance or rejection of change requests

## Slide 16
Change Management
Change Control Board – Tasks
Classify incoming changes
  For example, based on their criticality
Prioritize accepted change requests
  In which order should accepted changes be implemented?
Assign accepted change requests
  Who is responsible for implementing the changes?

## Slide 17
Change Management
Change Control Board – Members
The following parties should be represented in the change control board:
  Change manager
  Contractor
  Architect
  Developer
  Configuration manager
  Customer representative
  Product manager
  Project manager
  Quality assurance representative
  Requirements engineer

## Slide 18
Change Management
Change Control Board – Change Manager
Chairperson of the change control board
Mediates between parties in case of conflicts
Communicates and documents changes
Similar to the role of the requirements engineer

## Slide 19
Change Management
Change Requests
Should contain the following information:
Identifier
  Unique identification of change request possible
Title
  Summarizes key concern of the change request
Description
  Documents change as precisely as possible
  Also contains information on the expected effect of a change
Justification
  Reasons why the change is necessary
Date filed
  Date the change request was filed
Applicant
  Name of the person who filed the change request
Priority
  Importance of the change

## Slide 20
Change Management
Change Requests
Date filed
  Date the change request was filed
Applicant
  Name of the person who filed the change request
Priority
  Importance of the change

## Slide 21
Change Management
Change Requests
The following information is helpful for the management of changes:
Change validator
  Person who is responsible to verify if a change was performed correctly
Impact analysis status
  Flag indicating whether an impact analysis has been performed
Change control board decision status
  Flag indicating the handling status of the request
  For example: pending, rejected, accepted

## Slide 22
Change Management
Change Requests
Change control board priority
  Priority of the change request assigned by the change control board
Responsible
  Person in charge of performing the change
System release
  Version of the system that implements the change

## Slide 23
Change Management
Change Requests – Classifications
Three types of change requests:
Corrective requirement change
  Failure in the system
  Reason for failure is an error in the requirements
  Change fixes the error
Adaptive requirement change
  System needs to be amended
  For example, change in the system context or stakeholder needs
Exceptional change (hotfix)
  Must be immediately done at all costs
  Can be either adaptive or corrective
  Usually due to critical bugs

## Slide 24
Change Management
Handling Change Requests
Effort required for the change is estimated
Affected requirements are determined
  Includes new requirements
Development artifacts that need to be change are determined
Effort for artifact change usually significantly higher than for requirement changes
  Maintaining the requirements document is cheap
  Still often neglected
Can be supported by traceability information

## Slide 25
Change Management
Handling Change Requests
Change evaluation
  Costs and benefits are compared
  Available resources are considered
Prioritizing
  Importance of the change
Assigning
  System release for implementing is decided
Rejection
  If a change is rejected it is communicated

## Slide 26
Summary

## Slide 27
Summary
Requirements of complex projects need to be managed
Requirements can change throughout a project
Changes need to be structured and processed
Change management defines how change requests are handled
Change control board = Evaluates and approves/rejects changes
Handling change requests requires a process on its own

## Slide 28
Questions?